## Fresh Start Plan
LOCAL AREA #: 15
FRESH START GRANT LOCAL AREA IMPLEMENTATION PLAN
Planned Grant Activities and Enrollments
Service Type |  |  |  | Planned # Receiving This Service
Temporary Disaster Relief Employment
Career Services
Training Services |  |  |  | 1
Supportive Services
Total # of Participants Planned to be Served (unduplicated total for full grant period of performance) |  |  |  | 1
Cumulative Total # of Participants Planned to Be Served By the End of Each Quarter: | Q1: 1 Q2: 1 | Q3: 1 Q4: 1 Q5: 1 | Q6: | Q7: Q8:
Planned Number of Employers to Receive Business Services |  |  |  | n/a
PILLAR OF SUCCESS: STRONG LOCAL PARTNERSHIPS | Research potential partners in local area and establish an Opioid Workgroup or begin participating in a similar group that already exists. |  | STATE'S EXPECTED COMPLETION DATE | LOCAL AREA'S PLANNED START DATE | LOCAL AREA'S PLANNED COMPLETION DATE
A. Conduct research and outreach to additional potential partners to assist with grant implementation and service delivery. |  |  | 2022-05-06 | 2022-03-01 | ongoing
B. Initiate an opioid workgroup, join an existing workgroup, and/or partner with one or more agencies/entities. |  |  | 2022-05-06 | ongoing | ongoing
C. In the cell to the right, briefly describe what you learned about additional partnership opportunities, unmet needs the grant funding could address, an existing opioid workgroup, starting an opioid workgroup, and how you will move forward with current and new and partners. |  | Drug issues are not limited to opioids. It was difficult finding the groups and while there are services in the area to address opioid need, the spectrum of need is broad and the services are not commonly known to the public especially in the rural areas. More goups are emergining but getting them known and working to coordinate services and bring then to the community is still needed.
D. In the cells below, list which partners have been contacted, those you plan to contact, and the role of each partner in implementation of the Fresh Start Grant.
Partners Already Participating | Role Partner Will Play in the Fresh Start Grant Implementation (such as referring potential participants, providing outpatient mental health treatment, hiring participants in temporary disaster relief jobs, etc.)
Monroe-Hope Alliance | List of members attached. It is the drug abuse prevention coalition for Monroe County. Roles: Referral/assistance/outreach
Morgan | Merenda Bell from Allwell Roles: Referral/assistance/outreach
Morgan | Blake Kimes, Morgan Behavioral Health Roles: Referral/assistance/outreach
Noble | Noble CARES- Shawn Ray, Chair (please see list of members attached)
Washington | Drug task force (list attached) with workforce hub
Buckeye Hills Regional Development | Regional economic develop dist/Area Ag. on Aging - Subgrant to continue Resource Navigator
Additional Partners Planned to Be Contacted to Participate in Fresh Start | Planned or Desired Role Partner Will Play in Fresh Start Grant Implementation
ACTIVITIES SPECIFIC TO DOL FRESH START GRANT |  |  | STATE'S EXPECTED COMPLETION DATE | LOCAL AREA'S PLANNED START DATE | LOCAL AREA'S PLANNED COMPLETION DATE
A. Review which counties in your local area are assigned to Communities I - IX, based on the specific types of impacts of the opioid crisis | Review the types of temporary disaster-relief employment jobs that are approved for each Community to address the unique impacts of the opioid crisis in each Community. |  | 2022-05-06 | 2022-05-06 | 2022-05-06
| Review the types of occupations approved for each Community in which to provide training for individuals who answer "no" to the voluntary question about history of opioid use. |  | 2022-05-06 | 2022-05-06 | 2022-05-06
B. Establish the Fresh Start Grant service delivery plan for the local area | Determine which of the key strategies the local area will implement using the Fresh Start Grant funds: 1) Temporary disaster-relief employment; 2) Building the skilled workforce in professions impacting opioid crisis; 3) Reintegrating individuals impacted by opioids into the workforce; and/or 4) Engaging employers to become recovery-friendly workplaces. |  | 2022-05-06 | 2022-05-06 | 2022-05-06
C. Indicate which of the four key possible strategies the local area will implement
Strategy 1. Temporary disaster relief employment (Note - DOL and ODJFS consider this is a critical strategy to address the impacts of the opioid emergency. If a local area does not plan to implement this strategy, you must indicate why and provide justification to demonstrate the impacts are being addressed by another partner/entity or that other planned strategies are more urgent. | Yes/No/Still Under Consideration (If no, indicate why and provide justification.) YES | List the planned specific types of temporary disaster relief employment jobs, based on those approved for each Community in the local area: Areawide Opioid Resource Navigator responsible for: Development of resource database available resources for opioid treatment and recovery; Creation and implementation of a toll free opioid hotline and website; Marketing of services; Representation to WDB and on county drug/opioid coalition meetings and one-stop meetings. Assist individuals in recovery to reenter the workforce across the four-county service areas.
List the specific job sites planned/confirmed for temporary disaster relief employment, if implementing this strategy: Buckeye Hills Regional Economic District-Resource Navigator
Describe how your local area will conduct outreach to locate participants to receive this service: Continually updated Recovery resource database website started under Opioid3 grant; Marketing through flyers; participation at Community Events and Workforce Activities. Explore use of social media sites.
Strategy 2. Building the skilled workforce in professions that could impact the causes and treatment of the opioid crisis | Yes/No/Still Under Consideration No | Describe how your local area determined the most critical skill shortages in professions that could impact the causes and treatment of the opioid crisis based on those approved for each Community, if implementing this strategy:
List the planned specific types of occupations for which training will be provided to individuals who answer "no" or do not respond to the voluntary question about history of opioid use, based on professions approved for each Community:
Describe how your local area will conduct outreach to locate participants to receive this service:
Strategy 3. Reintegrating into employment individuals who have a history of opioid use or have a friend or family member with a history of opioid use. | Yes/No/Still Under Consideration No | If your area will implement this strategy, list the planned specific types of occupations for which occupational skills training will be provided to individuals who answer "yes" to the voluntary question about history of opioid use. (Note - Training in any in-demand occupation is allowable for these participants, including professions that could impact the causes and treatment of the opioid crisis.)
Describe how your local area will conduct outreach to locate participants to receive this service:
Strategy 4. Engaging employers to become recovery-friendly workplaces. (Note - this cannot be the only strategy implemented with grant funds.) | Yes/No/Still Under Consideration No | If your area will implement this strategy, describe how your local area will use grant funds to increase the number of recovery-friendly employers.
|  |  | STATE'S EXPECTED COMPLETION DATE | LOCAL AREA'S PLANNED START DATE | LOCAL AREA'S PLANNED COMPLETION DATE
D. POLICIES: Review your local area's current policies to determine if any revisions or new policies are needed to be more flexible, comprehensive, and responsive to the needs of individuals and employers impacted by opioids. |  |  | 2022-05-06 | 2022-05-06 | 2022-05-06
Make changes to policies or develop new policies specific to this grant, based on review of area's current policies | Policy Topic (list below) | Purpose of the Policy Change/Addition (list below) | 2022-06-30 | 2022-05-06 | 2022-05-06
| Assessment | Establish policy to identify early-on if an individual has a history of opioid use or has a family member or friend with a history of opioid use | 2022-06-30 | 2022-05-06 | 2022-05-06
| Documenting and Securing Confidential Health Information | Separately document disclosure about a history of opioid use or other health information and securely keep in a restricted area separate from WIOA intake and assessment forms | 2022-05-06 | 2022-05-06 | 2022-05-06
Other Policies the Local Area Plans to Change or Create (list in cells below):
E. SERVICES | Review local area current services and consider expanding to make them more flexible and responsive to needs of individuals and employers impacted by opioids |  | 2022-06-30 | ongoing | ongoing
| Securing and Restricting Confidential Information | This local area will establish (or has already established) a process to keep documentation separate from WIOA intake and assessment forms and ensure documentation is secure and restricted from unauthorized individuals | 2022-05-06 | 2022-05-06 | 2022-05-06
| Resource Room | The OhioMeansJobs center(s) in this local area will stock/has already stocked the following relevant resources regarding Crisis Hotlines; Substance Use Disorder Treatment Providers; Recovery Centers; etc.: | 2022-05-06 | 2022-05-06 | 2022-05-06
| Please list below the Target Audience for any new workshops you plan to conduct (such as the public, employers, individuals with opioid use disorder, family members or friends of individuals with opioid use disorder, etc.) | Please list planned Informative Workshops to be provided for the Target Audience identified in the column to the left:
| Youth in School Settings | School sponsored events |  | 2022-05-06 | ongoing
PILLAR OF SUCCESS: KNOWLEGEABLE STAFF | Expand the expertise of Board personnel, service providers, and partner staff members on issues related to opioid use disorder relevant to their job. |  | STATE'S EXPECTED COMPLETION DATE | LOCAL AREA'S PLANNED START DATE | LOCAL AREA'S PLANNED COMPLETION DATE
A. List the planned categories of staff who will be trained and the topics related to opioid use disorder in which they will be trained
Categories of Staff Such as Reception/Resource Room Staff, Case Managers, Business Services Staff, Supervisors/Managers, OhioMeansJobs Partner Staff, etc.) | Planned Training Topic or Title
All OhioMeansJobs center staff | "What's in your backpack? Explore Your Working Knowledge of Substance Use Disorder" | Virtual Teams training planned and conducted by ODJFS in partnership with Working Partners. An announcement and schedule will be published by 4/16/22. | 2022-06-14 | 2022-05-23 | 2022-06-30
PILLAR OF SUCCESS: HOLISTIC CARE MANAGEMENT |  |  | STATE'S EXPECTED COMPLETION DATE | LOCAL AREA'S PLANNED START DATE | LOCAL AREA'S PLANNED COMPLETION DATE
A. In the cell to the right, describe your plans to create a Care Management Team or similar group to review participant progress/needs and readiness for each service, including work experience, transitional job, or permanent employment. | Participant already hired. |  | 2022-06-30 | continuation from Opioid 3 Grant | 2023-05-31
B. In the cell to the right, describe your plans to develop operating methods to regularly review participant's status and needs with partners involved in each participant's services. | Participant is a work experience participant and is contacted bi-monthly to discuss her activities and experiences with relationship to the events currenlty happening. The participant has constant contact and availability to staff at Buckeye Hills Regional Council for any matters that she would come into contact with that would need immediate attention. |  | 2022-06-30 | ongoing | 2023-05-31
PILLAR OF SUCCESS: RECOVERY-FRIENDLY WORKPLACES
A. Conduct research to determine if there are existing employers known to hire individuals in recovery. |  |  | 2022-06-30 | 2022-05-06 | ongoing
B. In the cell to the right, briefly describe what you learned about recovery-friendly employers in your area and how you will work with employers to hire participants in recovery. |  | ongoing

## Noble CARES
Noble County CARES
community access resources education services
Members:
1) Amanda Tharp – Belmont Co BDD | atharp@bcbdd.org
2) Angela Ackley- FCFC Parent Rep | angela.ackley@roadrunner.com
3) Angela Crock – Business Owner caldwellfoodcenter@caldwellfoodcenter.com
4) Angie Feldner- NCHD Clinic Nurse | Angie.Feldner@noblecohd.org
5) Becky Hall (claricehall58@yahoo.com) | claricehall58@yahoo.com
6) Beth Warner – Noble Local School- Guid Couns | beth.warner@gozeps.org
7) Bonnie Carpenter- GMN Head Start | hsdirector@gmncac.org
8) Brad Peoples- Community Member | bradleyapeoples.bp@gmail.com
9) Brooke Yontz- NCHD Support Staff | Brooke.Yontz@noblecohd.org
10) B. Rutherford- Caldwell Schools- HS Principal | brutherford@caldwell.k12.oh.us
11) Corey Ball - DYS | Corey.Ball@dys.ohio.gov
12) Dan Leffingwell - Noble Local School Superint. | dan.leffingwell@gozeps.org
13) Derek Norman-Sheriff's Office deputynorman@noblecountysheriffsoffice.com
14) Diane Braden- Community Member | diane@teambraden.com
15) Edna Niswonger – Victom Advocate | advocate@noblecountyprosecutor.com
16) F. Allen Fraley -Noble Co. Chamber of Com & Tourism | allen@noblecountychamber.com
17) Gary Ricer- Director Community Action-GMN | ceo@gmncac.org
18) Gwynn Stewart- OSU Extension | stewart.1818@osu.edu
19) Halle Randles – Caldwell Schools Elem Principal | hrandles@caldwell.k12.oh.us
20) Jackie Wheeler – Community Member- Parent | 0712jmw@gmail.com
21) Jason Feldner- Mid East Career Center | jfeldner@mid-east.k12.oh.us
22) Jennifer Mackie – Early Head Start | ehsmgr@gmncac.org
23) Jennifer Van Fleet - | jvanfleet@guernseycountyhd.org
24) Jessica Perrin – Noble Correctional Inst. | jessica.perrin@odrc.state.oh.us
25) Jim Starr – United Ambulance | JStar@seormc.org
26) Jody Polen- Community Member | jodypolen_70@yahoo.com
27) John Powell- Minister Naz. Church | cameldriverjp@frontier.com
28) Jolene Williamson – NCHD | Jolene.Williamson@noblecohd.org
29) Jon Bates – Caldwell Mayor | mayorjbates@yahoo.com
30) Judy Weisend – FCFC Coordinator | judy.weisend@noblecohd.org
31) Justin Denius – Noble Local Schools HS Princ | justin.denius@gozeps.org
32) Kacey Cottrill – Caldwell Schools- Superint. | kcottrill@caldwell.k12.oh.us
33) Kathy Fetzer – Southeast OH Reg Med Center | kefetzer@seormc.org
34) Kelli Clark – Noble Co Children’s Services | kelli.clark@jfs.ohio.gov
35) Kelly Riddle – Noble Co Prosecutor | kelly@noblecountyprosecutor.com
36) Kirby Moore - NCHD | Kirby.Moore@noblecohd.org
37) Kris Presnell – Noble Co Sheriff’s Office | kpresnell@noblecountysheriffsoffice.com
38) Kyla Myers – Noble Co JFS | kyla.myers@jfs.ohio.gov
39) LaShona DeVolld– Noble Learning Center | noblekidz@yahoo.com
40) Latisha Giffin – Parent- FCFC Rep | tishajo1988@gmail.com
41) Lauren Moore – Noble Co Board DD | lmoore@bcbdd.org
42) Loretta Visger – Community Action | prevdr@gmncac.org
43) Marcia Murphy – Noble Local Schools | marcia.murphy@gozeps.org
44) Mark Johnson- NCHD | mark.johnson@noblecohd.org
45) Melissa King - CASA | melissa@noblecountyprosecutor.com
46) Mindy Cayton – Buckeye Hills | mcayton@buckeyehills.org
47) Mindy Lowe - Noble County DJFS | Mindy.Lowe@jfs.ohio.gov
48) Missy Fitzgerald- Noble Behav Health Choices | mfitzgerald@noblebhc.org
49) Misty Cromwell - Mental Health Recovery Board mistyc@mhrs.org
50) Nancy Snook - OSU Extension Noble County | snook.9@osu.edu
51) Noble County Commissioners | noblecom@frontier.com
52) Peggy Malcomb – Noble Co Board DD | pmalcomb@ncbdd.org
53) Phillip Theobald – Noble Local Schools | Philip.theobald@gozeps.org
54) Robert Pickenpaugh – Noble County Sheriff | sheriff@noblecountysheriffsoffice.com
55) Roger Birch- Mental Health & Rec Serv Board | rogerb2@MHRS.org
56) Sandy Doudna – Ohio Valley ESC | sandy.doudna@omeresa.net
57) Saroya Mulligan - DYS | saroya.mulligan@dys.ohio.gov
58) Shari Rayner- DON NCHD | Shari.Rayner@noblecohd.org
59) Shawn Ray – Health Comm. NCHD | Shawn.Ray@noblecohd.org
60) Stacy Hrinko – Journal Leader Newspaper | stacy@journal-leader.com
61) Stephanie Danford– Domestic Violence Advo | nfvc2@frontier.com
62) Steve Williams - Noble Co Board of DD | swilliams@bcbdd.org
63) Susan Haas – RN NCHD | Susan.Haas@noblecohd.org
64) Tabitha Weisend – Noble Co Board DD | tweisend@ncbdd.org
65) Tammy Stillion – Allwell Counseling Center | TStillion@allwell.org
66) Tiffany Speck – Caldwell Elem Principal | tspeck@caldwell.k12.oh.us
67) Tim Cunningham - DPS | TRCunningham@DPS.ohio.gov
68) United285mck- Ambulance Service | united285mck@yahoo.com

## Washington
Opioid Workforce Hub of Washington County
Committee members
Freimann, Flite H FLITE.FREIMANN@jfs.ohio.gov
belpremayor@wirefire.com;
Hughes, Hilles hhughes@wcbhb.org
EricBrockmeier@orianahouse.org;
Jesse Roush jroush1@wscc.edu
Robin Bozian rbozian@seols.org;
Tasha Werry twerry@mariettacsdoh.org
Tony Huffman thuffman@thecareercenter.net
Janice McFarland janicem@l-pservices.com
Doug douglasp@l-pservices.com
Karen Pawloski KPawloski@buckeyehills.org
Carrie Ankrom ankrom@mariettachamber.com
eml: MBrown 11/18/19